## User Stories
Requirement ID | User Story | Expected Time (hrs) | Actual Time (hrs) | Status
1.1 | Web Page is Displayed to the User | 1 | 1.5 | Complete
1.2 | Backend Responds to HTTP Requests | 2 | 1.5 | Complete
2.1 | Frontend Displays Data from the Backend | 1 | 1 | Complete
2.2 | Backend Returns Domain Specific Data | 2 | 0.5 | Complete
2.3 | Define Course Data Model | 5 | 4 | Complete
2.4 | Define Schedule Data Model | 2 | 1.5 | Complete
2.5 | Populate DB with Initial Data (Importing) | 5 | 4 | Complete
3.1 | Create a User | 3 | 2 | Complete
3.2 | Login as a User | 2 | 3 | Complete
3.3 | Save User Data (schedules/custom courses) | 3 | 2 | Complete
3.4 | Establish different levels of user roles (student/admin) | 2 | 1 | Complete
3.5 | Implement Role-Specific Behavior | 3 | 4 | Complete
4.1 | Identify Conflicts Between Selected Courses | 13 | 6 | Complete
4.2 | Ensure Class Data is Well-Formatted | 5 | 1 | Complete
4.3 | Save User Schedule | 2 | 2 | Complete
4.4 | Load User Schedule | 2 | 2 | Complete
4.5 | Search Course List | 3 | 1 | Complete
4.6 | Select Course from List | 3 | 1 | Complete
4.7 | Unselect Course from List | 3 | 1 | Complete
4.8 | Form all possible schedules | 5 | 5 | Complete
4.9 | Blacklist Times | 3 | 0 | Future Work
4.10 | Pin a Specific Instance of a Course | 3 | 0 | Future Work
4.11 | Add Custom Course | 5 | 23 | Complete
5.1 | Create Schedule Page Layout | 5 | 3 | Complete
5.2 | Create Dashboard Page Layout | 5 | 2 | Complete
5.3 | Create Login Page Layout | 2 | 1 | Complete
5.4 | Create Sign Up Page Layout | 2 | 1 | Complete
5.5 | Create Settings Page Layout | 3 | 3 | Complete
5.6 | Selected Classes Shown in a Sidebar | 3 | 0.5 | Complete
5.7 | Weekly Calendar Shows Selected Courses at Their Times | 8 | 1 | Complete
5.8 | Course Search | 8 | 0.5 | Complete
5.9 | View all possible schedules | 8 | 2 | Complete
6 | Documentation | 21 | 6.5 | Complete
7 | Research | 8 | 6 | Complete

## Group Meetings
Date | Meeting | Length (Hours)
2025-10-06 | GTA Meeting | 0.75
2025-10-08 | Discuss backend | 0.75
2025-10-20 | GTA Meeting | 0.5
2025-10-22 | Discuss Sprint 1 and Architecture | 1
2025-11-03 | GTA Meeting | 1
2025-11-05 | Sprint 2 Check-in | 1
2025-11-10 | Sprint 2 Release and Sprint 3 Planning | 1
2025-11-14 | GTA Meeting | 0.25
2025-11-17 | GTA Meeting | 0.75
2025-11-22 | Team Work Meeting | 1
2025-11-23 | Team Work Meeting/Sprint 3 Release | 2
2025-11-24 | Final GTA Meeting | 1

## Mohamed Ashraq
Date | Task Description | Time Worked (Hours)
2025-10-07 | Django Research | 3
2025-10-26 | UML Review | 0.15
2025-11-09 | Created scheduleGenerator.ts | 2
2025-11-09 | Updated schedulebulder.tsx to support features like selecting/unselecting | 4
2025-11-23 | Integrated course conflict | 6
2025-11-23 | Made schedule builder give all possible schedules | 5
2025-12-02 | Updated to be able to block the schedule when in conflict | 2
2025-12-03 | Presentation Record | 0.5

## Bryson Toubassi
Date | Task Description | Time Worked (Hours)
2025-10-13 | Django research | 0.5
2025-10-14 | Django research | 0.5
2025-10-24 | Backend UML Diagram | 1
2025-10-24 | Front UML Diagram | 1
2025-10-28 | Signup/Login Page | 2
2025-11-03 | Dashboard page | 1
2025-11-04 | Dashboard page | 1
2025-11-07 | Schedule Builder Page | 1
2025-11-09 | Schedule Builder Page | 2
2025-11-23 | Settings Page UI | 1
2025-11-23 | Settings Page backend | 2

## Owen Berkholtz
Date | Task Description | Time Worked
2025-10-17 | Django Research | 0.5
2025-10-25 | Architecture Description | 1
2025-11-09 | Merge and route Auth-pages, Schedule Builder, and Dashboard | 0.5
2025-11-17 | Create User data model for backend | 2
2025-11-17 | Allow users to sign up and add the new user to the database | 2
2025-11-17 | Allow users to log into the web application with an existing user | 0.5
2025-11-21 | Implement password recovery for users with an email | 1
2025-11-22 | Give users a session token when they log in | 1
2025-11-22 | Implement protected routes so user cannot access /dashboard and /builder without a token | 0.5
2025-11-22 | Touch up the UI | 1.5
2025-11-23 | Add conditional rendering based on if the user is a superuser | 1
2025-11-23 | Allow a superuser to elevate a user into a superuser | 3
2025-12-03 | Record Presentation | 0.5

## Matthew Eagleman
Date | Task Description | Time Worked
2025-10-19 | Django research | 0.2
2025-10-19 | added reference stories | 1
2025-10-26 | populate database with classes | 4
2025-11-09 | Django/React research | 2
2025-11-16 | Add ability to block out periods of time | 0.5
2025-11-17 | Add ability to block out periods of time | 1.75
2025-11-19 | Add Custom Courses/React Research | 2
2025-11-21 | Add Custom Courses | 4
2025-11-22 | Add Custom Courses | 8
2025-11-23 | Finished Adding Custom Courses | 9
2025-12-03 | Recording and editing presentation | 6.5

## Connor Anderson
Date | Task Description | Time Worked (Hours)
2025-10-07 | Initial Frontend and Repo Creation | 1.5
2025-10-12 | Django research | 1
2025-10-13 | Django research | 0.5
2025-10-13 | Initial Backend and Repo Creation | 2
2025-10-15 | Backend documentation | 0.5
2025-10-15 | Connect frontend to backend and update data models | 2
2025-10-16 | Requirements Engineering -- Finalize Course data model | 3
2025-10-16 | Start updating frontend to confirm to backend data model | 0.5
2025-10-22 | Project Architecture UML Diagrams | 0.25
2025-10-22 | Update Requirements Stack | 0.5
2025-10-26 | Convert the frontend to TypeScript from JavaScript | 1
2025-10-26 | UML Class Diagram | 1
2025-10-26 | Update and Upload Documenation to Repo | 0.5
2025-10-26 | Sprint 1 Artifacts Document | 0.5
2025-11-03 | Schedule Model | 1.5
2025-11-10 | Start Sprint 2 Release and Sprint 3 Initial Documents | 0.5
2025-11-12 | Update Course model and interface (remove warnings and update string repr) | 0.5
2025-11-12 | Add initial query abilities for Courses | 0.5
2025-11-16 | Update the frontend search to query the backend database | 0.5
2025-11-16 | Update api url paths to avoid duplicates | 0.25
2025-11-22 | DisplayCourses vs. Courses (Unify sections of the same course) | 3
2025-11-23 | Saving, Loading, and Updated User-Specific Schedules | 5
2025-11-23 | Documentation | 1.5
2025-12-02 | Presentation Slides | 1
2025-12-03 | Presentation Recording | 1.5