## Sheet1
Requirements No. | Requirement ID | Description | Points | Priority | Sprint No. | Complete
1 | 1.1 | Web Page is Displayed to the User | 1 | 1 | 1 | TRUE
2 | 1.2 | Backend Responds to HTTP Requests | 2 | 2 | 1 | TRUE
3 | 2.1 | Frontend Displays Data from the Backend | 1 | 3 | 1 | TRUE
4 | 2.2 | Backend Returns Domain Specific Data | 2 | 4 | 1 | TRUE
5 | 2.3 | Define Course Data Model | 5 | 5 | 1 | TRUE
6 | 2.4 | Define Schedule Data Model | 2 | 6 | 2 | TRUE
7 | 2.5 | Populate DB with Initial Data (Importing) | 5 | 7 | 1 | TRUE
8 | 3.1 | Create a User | 3 | 21 | 3 | TRUE
9 | 3.2 | Login as a User | 2 | 22 | 3 | TRUE
10 | 3.3 | Save User Data (schedules/custom courses) | 3 | 28 | 3 | TRUE
11 | 3.4 | Establish different levels of user roles (student/admin) | 2 | 25 | 3 | TRUE
12 | 3.5 | Implement Role-Specific Behavior | 3 | 26 | 3 | TRUE
13 | 4.1 | Identify Conflicts Between Selected Courses | 13 | 14 | 3 | TRUE
14 | 4.2 | Ensure Class Data is Well-Formatted | 5 | 29 | 3 | TRUE
15 | 4.3 | Save User Schedule | 2 | 23 | 3 | TRUE
16 | 4.4 | Load User Schedule | 2 | 24 | 3 | TRUE
17 | 4.5 | Search Course List | 3 | 16 | 2 | TRUE
18 | 4.6 | Select Course from List | 3 | 9 | 2 | TRUE
19 | 4.7 | Unselect Course from List | 3 | 10 | 2 | TRUE
20 | 4.8 | Form all possible schedules | 5 | 13 | 2 | TRUE
21 | 4.9 | Blacklist Times | 3 | 31 | Final | FALSE
22 | 4.10 | Pin a Specific Instance of a Course | 3 | 30 | Final | FALSE
23 | 4.11 | Add Custom Course | 5 | 27 | 3 | TRUE
24 | 5.1 | Create Schedule Page Layout | 5 | 8 | 2 | TRUE
25 | 5.2 | Create Dashboard Page Layout | 5 | 17 | 2 | TRUE
26 | 5.3 | Create Login Page Layout | 2 | 18 | 2 | TRUE
27 | 5.4 | Create Sign Up Page Layout | 2 | 19 | 2 | TRUE
28 | 5.5 | Create Settings Page Layout | 3 | 32 | 3 | TRUE
29 | 5.6 | Selected Classes Shown in a Sidebar | 3 | 11 | 2 | TRUE
30 | 5.7 | Weekly Calendar Shows Selected Courses at Their Times | 8 | 12 | 2 | TRUE
31 | 5.8 | Course Search | 8 | 20 | 2 | TRUE
32 | 5.9 | View all possible schedules | 8 | 18 | 2 | TRUE
33 | 6 | Documentation | 21 | 33 | All | TRUE
34 | 7 | Research | 8 | 34 | All | TRUE