## User Stories
Requirement ID | User Story | Expected Time (hrs) | Actual Time (hrs) | Status
1.1 | Web Page is Displayed to the User | 1 | 1.5 | Complete
1.2 | Backend Responds to HTTP Requests | 2 | 1.5 | Complete
2.1 | Frontend Displays Data from the Backend | 1 | 1 | Complete
2.2 | Backend Returns Domain Specific Data | 2 | 0.5 | Complete
2.3 | Define Course Data Model | 5 | 4 | Complete
2.4 | Define Schedule Data Model | 2 | 1.5 | Complete
2.5 | Populate DB with Initial Data (Importing) | 5 | 4 | Complete
3.1 | Create a User | 3
3.2 | Login as a User | 2
3.3 | Save User Data (schedules/custom courses) | 3
3.4 | Establish different levels of user roles (student/admin) | 2
3.5 | Implement Role-Specific Behavior | 3
4.1 | Identify Conflicts Between Selected Courses | 13
4.2 | Ensure Class Data is Well-Formatted | 5
4.3 | Save User Schedule | 2
4.4 | Load User Schedule | 2
4.5 | Search Course List | 3
4.6 | Select Course from List | 3
4.7 | Unselect Course from List | 3
4.8 | Form all possible schedules | 5
4.9 | Blacklist Times | 3
4.10 | Pin a Specific Instance of a Course | 3
4.11 | Add Custom Course | 5
5.1 | Create Schedule Page Layout | 5 | 3 | Complete
5.2 | Create Dashboard Page Layout | 5 | 2 | Complete
5.3 | Create Login Page Layout | 2 | 1 | Complete
5.4 | Create Sign Up Page Layout | 2 | 1 | Complete
5.5 | Create Settings Page Layout | 3
5.6 | Selected Classes Shown in a Sidebar | 3 | 0.5 | Complete
5.7 | Weekly Calendar Shows Selected Courses at Their Times | 8 | 1 | Complete
5.8 | Course Search | 8 | 0.5 | Complete
5.9 | View all possible schedules | 8 | 2 | Complete
6 | Documentation | 21 | 4
7 | Research | 8

## Mohamed Ashraq
Date | Task Description | Time Worked (Hours)
2025-10-07 | Django Research | 1
2025-10-26 | UML Review | 0.15
2025-11-09 | Created scheduleGenerator.ts | 2
2025-11-09 | Updated schedulebulder.tsx to support features like selecting/unselecting | 4

## Group Meetings
Date | Meeting | Length (Hours)
2025-10-06 | GTA Meeting | 0.75
2025-10-08 | Discuss backend | 0.75
2025-10-20 | GTA Meeting | 0.5
2025-10-22 | Discuss Sprint 1 and Architecture | 1
2025-11-03 | GTA Meeting | 1
2025-11-05 | Sprint 2 Check-in | 1
2025-11-10 | Sprint 2 Release and Sprint 3 Planning | 1

## Bryson Toubassi
Date | Task Description | Time Worked (Hours)
2025-10-13 | Django research | 0.5
2025-10-14 | Django research | 0.5
2025-10-24 | Backend UML Diagram | 1
2025-10-24 | Front UML Diagram | 1
2025-10-28 | Signup/Login Page | 2
2025-11-03 | Dashboard page | 1
2025-11-04 | Dashboard page | 1
2025-11-07 | Schedule Builder Page | 1
2025-11-09 | Schedule Builder Page | 2

## Matthew Eagleman
Date | Task Description | Time Worked
2025-10-19 | Django research | 0.2
2025-10-19 | added reference stories | 1
2025-10-26 | populate database with classes | 4
2025-11-09 | Django/React research | 2

## Owen Berkholtz
Date | Task Description | Time Worked
2025-10-17 | Django Research | 0.5
2025-10-25 | Architecture Description | 1
2025-11-09 | Merge and route Auth-pages, Schedule Builder, and Dashboard | 0.5

## Connor Anderson
Date | Task Description | Time Worked (Hours)
2025-10-07 | Initial Frontend and Repo Creation | 1.5
2025-10-12 | Django research | 1
2025-10-13 | Django research | 0.5
2025-10-13 | Initial Backend and Repo Creation | 2
2025-10-15 | Backend documentation | 0.5
2025-10-15 | Connect frontend to backend and update data models | 2
2025-10-16 | Requirements Engineering -- Finalize Course data model | 3
2025-10-16 | Start updating frontend to confirm to backend data model | 0.5
2025-10-22 | Project Architecture UML Diagrams | 0.25
2025-10-22 | Update Requirements Stack | 0.5
2025-10-26 | Convert the frontend to TypeScript from JavaScript | 1
2025-10-26 | UML Class Diagram | 1
2025-10-26 | Update and Upload Documenation to Repo | 0.5
2025-10-26 | Sprint 1 Artifacts Document | 0.5
2025-11-03 | Schedule Model | 1.5
2025-11-10 | Start Sprint 2 Release and Sprint 3 Initial Documents | 0.5