## Sheet1
Requirements No. | Requirement ID | Description | Points | Priority | Sprint No.
1 | 1.1 | Web Page is Displayed to the User | 1 | 1
2 | 1.2 | Backend Responds to HTTP Requests | 2 | 2
3 | 2.1 | Frontend Displays Data from the Backend | 1 | 3
4 | 2.2 | Backend Returns Domain Specific Data | 2 | 4
5 | 2.3 | Define Data Models | 13 | 5
6 | 2.4 | Populate DB with Initial Data (Importing) | 5 | 6
7 | 3.1 | Create a User | 3 | 16
8 | 3.2 | Login as a User | 2 | 17
9 | 3.3 | Save User Data (schedules/custom courses) | 3 | 23
10 | 3.4 | Establish different levels of user roles (student/admin) | 2 | 20
11 | 3.5 | Implement Role-Specific Behavior | 3 | 21
12 | 4.1 | Identify Conflicts Between Selected Courses | 13 | 12
13 | 4.2 | Ensure Class Data is Well-Formatted | 5 | 24
14 | 4.3 | Save User Schedule | 2 | 18
15 | 4.4 | Load User Schedule | 2 | 19
16 | 4.5 | Search Course List | 3 | 14
17 | 4.6 | Select Course from List | 3 | 7
18 | 4.7 | Unselect Course from List | 3 | 8
19 | 4.8 | Form all possible schedules | 5 | 11
20 | 4.9 | Blacklist Times | 3 | 26
21 | 4.10 | Pin a Specific Instance of a Course | 3 | 25
22 | 4.11 | Add Custom Course | 5 | 22
23 | 5.1 | Selected Classes Shown in a Sidebar | 3 | 9
24 | 5.2 | Weekly Calendar Shows Selected Courses at Their Times | 8 | 10
25 | 5.3 | Course Search | 8 | 15
26 | 5.4 | View all possible schedules | 8 | 13